## Weekly Plan
| Service Management/Health (0) | Account support (0) | Service Delivery (0) | IP Development (0) | Mentorship (0)
PRIORITY | Service A (example only) - Weekly Catchup - Document Reviews - SDS Review Service B (example only) - Process Reviews Service C (example only) - Requirements finalisation and next steps - SDS | Priority Framework overview with X Priority Framework Prep forY CX Client Service presentation and next steps Service Confirmation with Y |  | - IP Item A - IP Item B - IP Item C - IP Item D - IP Item E | Consultant 1 - Monthly Consultant 2 - Monthly Consultant 3 - Monthly Consultant 4 - Monthly Consultant 5 - Monthly Consultant 6 - Monthly
| PEOPLE TO CONNECT WITH |  |  | Key Stats
| Client - Name- Role |  |  | Number of Services as Lead BA : | 4
| Client - Name- Role |  |  | Number of Service Consultants : | 8
| Client - Name- Role |  |  | Mentees (All BAPL) : | 6
| Client - Name- Role |  |  | Lead Consultant non-Billable days/week : | 3
Client - Name- Role

## Dashboard
# | Organisation | Service | Consultant | End Date | Ext? | Value Statement | SDS | Workplan | Status Updates | Consultant | Client | Lead | Current Deliverable | Overall Comments
1 | Client A | Service Name A | 0 | 2025-03-31 | 0 | 0 | Red | Red | Red | Red | Red | Red | Other - | 0
2 | Client B | Service Name B | 0 | 2025-09-11 | 0 | 0 | Red | Red | Red | Red | Red | Red | Other - | 0
3
4
5
6
7
8
9
10
11
12
13
14
15
End Date
| 2025-04-17 | Date Within 30 Days
| 2025-06-16 | Date within 90 Days
Formulas:
End Date = IFERROR(INDIRECT("'"&[Service]&"'!$D4"),"")

## SAP AMS (hidden)
Consultant: | Jeanne | Project: | SAP AMS
Notes | Recurring Notes for Cleanco
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes | Part of the Cyber Uplift
| Are weekly status reports sent | Yes | Part of the Cyber Uplift
| Is Status Report saved | Yes | Part of the Cyber Uplift
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Complete - Service Complete
| Current Project State | Complete
| Deliverable currently being worked on | Service Complete
Overall Notes/Comments

## LearnJCU Enhancements (hidden)
Consultant: | Ami | Project: | LearnJCU Enhancements
Notes | https://docs.google.com/presentation/d/1x_6DNXXpOJOX_hkUjiWOdytpUaK40jTk4DeQlVd6pYo/edit#slide=id.g2ad1a9a4709_0_0
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Complete - Service complete
| Current Project State | Complete
| Deliverable currently being worked on | Service complete
Overall Notes/Comments

## SkillsJCU SMS Integration (hidden)
Consultant: | Bryant | Project: | SkillsJCU SMS Integration
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Complete - Service Complete
| Current Project State | Complete
| Deliverable currently being worked on | Service Complete
Overall Notes/Comments

## App Backlog Refinement (hidden)
Consultant: | Ami | Project: | App Backlog Refinement
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Complete - Service Complete
| Current Project State | Complete
| Deliverable currently being worked on | Service Complete
Overall Notes/Comments

## Data Attributes (hidden)
Data Fields
Google drives
Yes
No
Performance
Yes
No
Needs Assistance
Current Project State
Current
Future
Gap
Recommendation
Other
Complete
Value Statement
None
Needs Work
Ok
Good
Great

## OLD Project View (hidden)
Consultant: | Dave & Arlene | Project: | Curriculum Blueprint
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Dave | Project: | VET Clusters
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | No
| Are weekly status reports sent | No | No updates
| Is Status Report saved | No
Consultant Performance
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Dave | Project: | AIMS Leaderships
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | No
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Dave | Project: | BA templates
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Dave | Project: | Community of Practice
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | No | Internal BA's still working out scope
| Is Work Plan saved | No | Has not started due to project still being worked on
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Arlene | Project: | VET Apprentice Block
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Louis | Project: | Grow Students
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | No
| Are weekly status reports sent | Yes
| Is Status Report saved | No
Consultant Performance
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Paritosh | Project: | My Study Works
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Paritosh | Project: | Labour Market Insights
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Paritosh | Project: | Credentialate
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Paritosh | Project: | CQU Success
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Paritosh | Project: | My Experience
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | NEEDs assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Neha | Project: | Research Master
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Neha | Project: | Data Management Processes
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Neha | Project: | Data Management Catalogue
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Neha | Project: | Social Media Prospect Log In
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | No
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Thao and Urusa | Project: | Digital Experience Platform
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Bryant | Project: | Ticketing System
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Consultant: | Bansri | Project: | VET Fee Calculator
BAPL delivery documentation on google drive |  | Yes/No | Comments
| Is SDS saved | No
| Is Work Plan saved | No
| Are weekly status reports sent | No
| Is Status Report saved | No
Consultant Performance
| Is the consultant deliverables of quality | Needs Assistance
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
| Does the consultant have personal issues which can impact the project | Yes
Client Performance
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes

## OLD High Level (hidden)
RAG Status
Consultant | Project | BAPL delivery documentation on google drive | Consultant Performance | Client Performance
Dave and Arlene | Curriculum Blueprint | Green | Orange | Green
Dave | VET Clusters | Red | Red | Green
| AIMS leadership | Green | Red | Green
| BA templates | Green | Red | Green
| Community of Practice | Red | Red | Green
Arlene | VET Apprentice Block | Green | Red | Green
Louis | Grow Students | Red | Red | Green
Paritosh | MSW | Green | Red | Green
| LMI | Green | Red | Green
| Credentialate | Green | Red | Green
| CQU Success | Green | Red | Green
| MyExperience | Green | Red | Green
Neha | Research | Green | Red | Green
| Data Management Processes | Green | Red | Green
| Data Management Catalogue | Green | Red | Green
| Social Media Prospect Log In | Red | Red | Green
Thao and Urusa | Digital Experience Platform | Green | Red | Green
Bryant | Ticketing System | Green | Red | Green
Bansri | VET Fee Calculator | Red | Red | Green

## CAPS (hidden)
Consultant | Vandana | Service | Comments | Service Days | Date Updated | Total Days Worked | Days Remaining
Service Overview |  |  |  | 206 | 2024-11-15 | 202.25 | 3.75
| Service End Date | 2024-11-21 | Updated due to Sick Leave
| What's next? | End Service | CQU have requested to have Vandana again next year.
| Are We Seeking a Referral for this Service? When, How? | Not currently. | Referral requested from the business side - Christina Hong. |  | Date Updated | Total Days Worked | Days Remaining
| Is the value statement specific and measureable? | Ok |  |  | 2024-10-04 | 175.25 | 30.75
SDS |  | Green |  |  | 2024-10-18 | 184.25 | 21.75
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes |  |  | 2024-11-01 | 193.25 | 12.75
| Are key activities and expected deliverables defined and up to date? | Yes |  |  | 2024-11-15 | 202.25 | 3.75
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes
Workplan |  | Green
| Is the service on track to deliver on purpose and value? | Yes
| Is the next fortnight of tasks captured in the workplan? | Yes | Planned for remainder of service.
| Are the known issues and risks captured? | Yes
Status Updates |  | Green
| Are status reports sent to client, lead and SM weekly? | Yes
| Are status reports saved in google drive? | Yes
| Is there an recurring meeting for updates? | Yes
Consultant |  | Green
| Are deliverables being updated based on feedback? | Yes
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes
Current Deliverable |  | Future - Entry Req changes, Eng Lang Prof, Pre-Reqs, Checkpoint Checklists
| Current Project State | Future
| Deliverable currently being worked on | Entry Req changes, Eng Lang Prof, Pre-Reqs, Checkpoint Checklists
| Overall Comments | Wrapping up this week.
Consultant Coaching/Mentoring Needs
Nothing particular at this stage
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date | Org Chart Updated Sep-24
Action / Date
Action / Date
Note on C26: For example: SME's are approachable and provide information

## CTS (hidden)
Consultant | Paritosh | Service | Comments | Service Days | Date Updated | Total Days Worked | Days Remaining
Service Overview |  |  |  | 45.5 | 2024-11-29 | 32 | 13.5
| Service End Date | 2024-12-19 | (Includes CSM) Awaiting PO details for extension.
| What's next? | Extension approved. | CQU have requested to have Paritosh again next year.
| Are We Seeking a Referral for this Service? When, How? | Not currently. | Some great feedback so far from Project Sponsor. Will involve in referral in future months. |  | Date Updated | Total Days Worked | Days Remaining
| Is the value statement specific and measureable? | Needs Work | Paritosh currently reviewing as service in final week. |  | 2024-10-04 | 0 | 45.5
SDS |  | Green |  |  | 2024-10-18 | 2 | 43.5
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes |  |  | 2024-11-01 | 12 | 33.5
| Are key activities and expected deliverables defined and up to date? | Yes |  |  | 2024-11-15 | 22 | 23.5
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes |  |  | 2024-11-29 | 32 | 13.5
Workplan |  | Green
| Is the service on track to deliver on purpose and value? | Yes
| Is the next fortnight of tasks captured in the workplan? | Yes
| Are the known issues and risks captured? | Yes
Status Updates |  | Green
| Are status reports sent to client, lead and SM weekly? | Yes
| Are status reports saved in google drive? | Yes
| Is there an recurring meeting for updates? | Yes
Consultant |  | Green
| Are deliverables being updated based on feedback? | Yes
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes
Current Deliverable |  | Recommendation - Close Out next week, putting together recommendation.
| Current Project State | Recommendation
| Deliverable currently being worked on | Close Out next week, putting together recommendation.
| Overall Comments | Meeting this afternoon (13-Dec) to discuss final deliverables and priority.
Consultant Coaching/Mentoring Needs
Nothing particular at this stage
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date | Org Chart Updated Sep-24
Action / Date
Action / Date
Note on C26: For example: SME's are approachable and provide information

## SBPA v2 (hidden)
Consultant | Paritosh | Service | Comments
Service Overview
| Service End Date | 2024-12-19
| What's next? | COMPLETE
| Are We Seeking a Referral for this Service? When, How? | No
| Is the value statement specific and measureable? | Ok | Not really a service I'd expect another client to need - it's more of a "partner assistance" type piece of work.
SDS |  | Green
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes | Small piece of work of a few days that's a continuation/extension of previous SDS
| Are key activities and expected deliverables defined and up to date? | Yes
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes
Workplan |  | Green | Workplan is combined within CTS Work Plan
| Is the service on track to deliver on purpose and value? | Yes
| Is the next fortnight of tasks captured in the workplan? | Yes
| Are the known issues and risks captured? | Yes
Status Updates |  | Green
| Are status reports sent to client, lead and SM weekly? | Yes
| Are status reports saved in google drive? | Yes
| Is there a recurring meeting for updates? | Yes
Consultant |  | Green
| Are deliverables being updated based on feedback? | Yes
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes
Current Deliverable |  | Complete - Service Complete
| Current Project State | Complete
| Deliverable currently being worked on | Service Complete
| Overall Comments | Client very happy.
Consultant Coaching/Mentoring Needs
I have had real .. Problems (minor) with communication with Bansri. On several occasions she seems to contradict herself leading to confusion. Most recent instance was her saying "The files are on the CQU drive" but then also saying "Yes" to the files are in her own personal folder. Another being a Process Model was a Future State Model wasn't Future State, it was Current State how they thought it should work. I don't know if it's just me, but I have found myself struggling on my occasions and having long conversations just to understand some detail. Could totally be a "me" thing, just worth nothing if the trend continues in future services.
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date | Org Chart Updated Sep-24
Action / Date
Action / Date

## CSM (hidden)
Consultant | Paritosh | Service | Comments | Service Days | Date Updated | Total Days Worked | Days Remaining
Service Overview |  |  |  | 126 | 2024-10-18 | 126 | 0
| Service End Date | 2024-11-01
| What's next? | Service has "closed". This is extra work. | CQU have requested to have Paritosh again next year.
| Are We Seeking a Referral for this Service? When, How? | Not currently. | Service is looking to continue next year. Details to be discussed mid/end November. |  | Date Updated | Total Days Worked | Days Remaining
| Is the value statement specific and measureable? | Great |  |  | 2024-10-04 | 119 | 7
SDS |  | Green |  |  | 2024-10-18 | 126 | 0
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes
| Are key activities and expected deliverables defined and up to date? | Yes
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes
Workplan |  | Green
| Is the service on track to deliver on purpose and value? | Yes
| Is the next fortnight of tasks captured in the workplan? | Yes
| Are the known issues and risks captured? | Yes
Status Updates |  | Green
| Are status reports sent to client, lead and SM weekly? | Yes
| Are status reports saved in google drive? | Yes
| Is there an recurring meeting for updates? | Yes
Consultant |  | Green
| Are deliverables being updated based on feedback? | Yes
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes
Current Deliverable |  | Future - Process Maps and Workload Allocation Review
| Current Project State | Future
| Deliverable currently being worked on | Process Maps and Workload Allocation Review
| Overall Comments | Final Deliverable to be reviewed and closed next week.
Consultant Coaching/Mentoring Needs
Nothing particular at this stage
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date | Org Chart Updated Sep-24
Action / Date
Action / Date

## Staff Business Process Auto (hidden)
Consultant | Bansri | Service | Comments
Service Overview
| Service End Date | 2024-10-01
| What's next? | Service Ending
| Are We Seeking a Referral for this Service? When, How? | No
| Is the value statement specific and measureable? | Ok | Not really a service I'd expect another client to need - it's more of a "partner assistance" type piece of work.
SDS |  | Green
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes
| Are key activities and expected deliverables defined and up to date? | Yes
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes
Workplan |  | Green
| Is the service on track to deliver on purpose and value? | Yes
| Is the next fortnight of tasks captured in the workplan? | Yes
| Are the known issues and risks captured? | Yes
Status Updates |  | Green
| Are status reports sent to client, lead and SM weekly? | Yes
| Are status reports saved in google drive? | Yes
| Is there a recurring meeting for updates? | Yes
Consultant |  | Green
| Are deliverables being updated based on feedback? | Yes
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes
Current Deliverable |  | Future - Requirements doc for Developers
| Current Project State | Future
| Deliverable currently being worked on | Requirements doc for Developers
| Overall Comments | Project wrapping up in a few days (Bansri has AL for 3 days this week 25-Sep).
Consultant Coaching/Mentoring Needs
I have had real .. Problems (minor) with communication with Bansri. On several occasions she seems to contradict herself leading to confusion. Most recent instance was her saying "The files are on the CQU drive" but then also saying "Yes" to the files are in her own personal folder. Another being a Process Model was a Future State Model wasn't Future State, it was Current State how they thought it should work. I don't know if it's just me, but I have found myself struggling on my occasions and having long conversations just to understand some detail. Could totally be a "me" thing, just worth nothing if the trend continues in future services.
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date | Org Chart Updated Sep-24
Action / Date
Action / Date

## Finance System Replacement (hidden)
Consultant | Roberto | Service | Comments | Service Days | Date Updated | Total Days Worked | Days Remaining
Service Overview |  |  |  | 42 | 2024-10-31 | 42 | 0
| Service End Date | 2024-10-31
| What's next? | End of service. | Will meet in Mid December to talk about next year. This year they will select vendor, get contract rolling etc.
| Are We Seeking a Referral for this Service? When, How? | Not at this early stage. |  |  | Date Updated | Total Days Worked | Days Remaining
| Is the value statement specific and measureable? | Ok | System won't be implemented through service. Requirements based on external company, not our own analysis (Client has accepted risk). Benefits of the service were reviewed and agreed to by PM on 11-Sep |  | 2024-10-11 | 28 | 14
SDS |  | Green |  |  | 2024-10-18 | 33 | 9
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes
| Are key activities and expected deliverables defined and up to date? | Yes
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes
Workplan |  | Green
| Is the service on track to deliver on purpose and value? | Yes
| Is the next fortnight of tasks captured in the workplan? | Yes
| Are the known issues and risks captured? | Yes
Status Updates |  | Green
| Are status reports sent to client, lead and SM weekly? | Yes
| Are status reports saved in google drive? | Yes
| Is there a recurring meeting for updates? | Yes
Consultant |  | Green
| Are deliverables being updated based on feedback? | Yes
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes | Also weekly meetings with PM and Henry
Current Deliverable |  | Future - Finalising current state and working on Future State for EOM/EOFY Processes
| Current Project State | Future
| Deliverable currently being worked on | Finalising current state and working on Future State for EOM/EOFY Processes
| Overall Comments | Client well aware and accepted risk in relation to utilising existing requirements.
Consultant Coaching/Mentoring Needs
Quality of documentation highlighted. Spelling/layout/consistency etc.
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date
Action / Date
Action / Date
Quality of documentation highlighted. Spelling/layout/consistency etc.

## Snap, Send, Solve (hidden)
Consultant | Ivor | Service | Comments | Service Days | Date Updated | Total Days Worked | End Date Variance
Service Overview |  |  |  | 42 | 2024-12-13 | 109.75 | -3.25
| Service End Date | 2024-12-20
| What's next? | No plans at this stage. | May be an update at the end of the month. Some other projects may come up re: Health and Safety system.
| Are We Seeking a Referral for this Service? When, How? | Not currently. |  |  | Date Updated | Total Days Worked | End Date Variance
| Is the value statement specific and measureable? | Ok | Potentially will adjust scope once further details in relation to Translink are established (such as levels of Stakeholder engagement and overlap with existing mapping) |  | 2024-09-20 | 54 | 0
SDS |  | Green |  |  | 2024-10-11 | 67 | -1
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes |  |  | 2024-10-18 | 72 | -1 | 5
| Are key activities and expected deliverables defined and up to date? | Yes |  |  | 2024-11-08 | 85.75 | -2.25 | 13.75
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes |  |  | 2024-11-15 | 90.75 | -2.25 | 5
Workplan |  | Green |  |  | 2024-11-22 | 94.75 | -3.25 | 4 | AL 18-Nov
| Is the service on track to deliver on purpose and value? | Yes |  |  | 2024-12-13 | 109.75 | -3.25 | 15
| Is the next fortnight of tasks captured in the workplan? | Yes | [5 empty] | -109.75
| Are the known issues and risks captured? | Yes | [5 empty] | 0
Status Updates |  | Green
| Are status reports sent to client, lead and SM weekly? | Yes
| Are status reports saved in google drive? | Yes
| Is there an recurring meeting for updates? | Yes
Consultant |  | Green
| Are deliverables being updated based on feedback? | Yes
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes
Current Deliverable |  | Complete - Finalising for close out this week.
| Current Project State | Complete
| Deliverable currently being worked on | Finalising for close out this week.
| Overall Comments | Client wants Ivor to return next year, Charissa in contact with client, awaiting further details by 20-Dec.
Consultant Coaching/Mentoring Needs
Nothing particular at this stage
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date
Action / Date
Action / Date

## Service Name A
Consultant |  | Service | Comments | Service Days | Date Updated | Total Days Worked | Days Remaining
Service Overview |  |  |  | 126 | 0 | 0 | 0
| Service End Date | 2025-03-31
What's next?
| Are We Seeking a Referral for this Service? When, How? |  |  |  | Date Updated | Total Days Worked | Days Remaining
Is the value statement specific and measureable?
SDS |  | Red | [5 empty] | 0
| Is the problem statement, service objectives and service outcomes clearly defined and current? | [6 empty] | 0
| Are key activities and expected deliverables defined and up to date? | [6 empty] | 0
| Is the latest SDS approved with screenshots of approval in the google drive? | [6 empty] | 0
Workplan |  | Red | [5 empty] | 0
| Is the service on track to deliver on purpose and value? | [6 empty] | 0
| Is the next fortnight of tasks captured in the workplan? | [6 empty] | 0
| Are the known issues and risks captured? | [6 empty] | 0
Status Updates |  | Red | [5 empty] | 0
| Are status reports sent to client, lead and SM weekly? | [6 empty] | 0
Are status reports saved in google drive?
Is there an recurring meeting for updates?
Consultant |  | Red
Are deliverables being updated based on Lead and Cleint feedback?
Do they have a good professional attitude?
Can the they facilitate on their own?
Client |  | Red
Is the client providing positive feedback regarding the service?
Has the client identified any areas of improvement or ares to be addressed?
Lead |  | Red
Are recurring meetings set up with the consultant?
Current Deliverable |  | Other -
| Current Project State | Other
Deliverable currently being worked on
Overall Comments
Consultant Coaching/Mentoring Needs
Nothing particular at this stage
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date | Org Chart Updated Sep-24
Action / Date
Action / Date
Formulas:
Date Updated = '[1]3 Work Plan'!$H2

## Service Name B
Consultant |  | Service | Comments | Service Days | Date Updated | Total Days Worked | Days Remaining
Service Overview |  |  |  | 126 | 0 | 0 | 0
| Service End Date | 2025-09-11
What's next?
| Are We Seeking a Referral for this Service? When, How? |  |  |  | Date Updated | Total Days Worked | Days Remaining
Is the value statement specific and measureable?
SDS |  | Red | [5 empty] | 0
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes | [5 empty] | 0
| Are key activities and expected deliverables defined and up to date? | Yes | [5 empty] | 0
| Is the latest SDS approved with screenshots of approval in the google drive? | [6 empty] | 0
Workplan |  | Red | [5 empty] | 0
| Is the service on track to deliver on purpose and value? | [6 empty] | 0
| Is the next fortnight of tasks captured in the workplan? | [6 empty] | 0
| Are the known issues and risks captured? | [6 empty] | 0
Status Updates |  | Red | [5 empty] | 0
| Are status reports sent to client, lead and SM weekly? | [6 empty] | 0
Are status reports saved in google drive?
Is there an recurring meeting for updates?
Consultant |  | Red
Are deliverables being updated based on feedback?
Do they have a good professional attitude?
Can the they facilitate on their own?
Client |  | Red
Does the Project Manager assist the consultant?
Is the client culture up to BAPL standards?
Lead |  | Red
Are recurring meetings set up with the consultant?
Current Deliverable |  | Other -
| Current Project State | Other
Deliverable currently being worked on
Overall Comments
Consultant Coaching/Mentoring Needs
Nothing particular at this stage
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date | Org Chart Updated Sep-24
Action / Date
Action / Date
Formulas:
Date Updated = '[1]3 Work Plan'!$H2

## Maturity Uplift (hidden)
Consultant | Jeanne | Service | Comments
Service Overview
| Service End Date | 2024-12-16
| What's next? | Nothing as yet. | Several very early ideas around uplift/training/template updates etc. may be future opportunities.
| Are We Seeking a Referral for this Service? When, How? | No - first few days
| Is the value statement specific and measurable? | Ok | The service is about recommendations for future uplift. As the service matures I would think fleshing this out without a explicit quantifiable benefit would still make for a strong referral opportunity.
SDS |  | Green
| Is the problem statement, service objectives and service outcomes clearly defined and current? | Yes
| Are key activities and expected deliverables defined and up to date? | Yes
| Is the latest SDS approved with screenshots of approval in the google drive? | Yes | Only initial signed SDS at this stage.
Workplan |  | Green
| Is the service on track to deliver on purpose and value? | Yes
| Is the next fortnight of tasks captured in the workplan? | Yes
| Are the known issues and risks captured? | Yes
Status Updates |  | Red
| Are status reports sent to client, lead and SM weekly? |  | First days of service, no reports yet
Are status reports saved in google drive?
Is there an recurring meeting for updates?
Consultant |  | Red
Are deliverables being updated based on feedback?
| Do they have a good professional attitude? | Yes
| Can the they facilitate on their own? | Yes
Client |  | Green
| Does the Project Manager assist the consultant? | Yes
| Is the client culture up to BAPL standards? | Yes
Lead |  | Green
| Are recurring meetings set up with the consultant? | Yes
Current Deliverable |  | Current - Discovery and Current State / SWOT Analysis
| Current Project State | Current
| Deliverable currently being worked on | Discovery and Current State / SWOT Analysis
| Overall Comments | First days of service
Consultant Coaching/Mentoring Needs
Nothing particular at this stage
Org Chart - Review our Breadth of Partnership and Growth Plan | Action/ Date
Action / Date
Action / Date
Action / Date

## Academy Process Improvement (hidden)
Consultant: | Bryant | Project: | Academy Process Improvement
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Complete - Service Complete
| Current Project State | Complete
| Deliverable currently being worked on | Service Complete
Overall Notes/Comments

## Research Master DONE (hidden)
Consultant: | Neha | Project: | Research Master DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Current - As-is High Level Process Map overview
| Current Project State | Current
| Deliverable currently being worked on | As-is High Level Process Map overview
| Overall Notes/Comments | 30-Oct Close Out meeting with David R | 20-Oct Feedback received from Paul H for Neha in general

## Data Management Processes DONE (hidden)
Consultant: | Neha | Project: | Data Management Processes DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Future - To-Be Process for Data Approval Form and Monitor/Control Data
| Current Project State | Future
| Deliverable currently being worked on | To-Be Process for Data Approval Form and Monitor/Control Data
| Overall Notes/Comments | 1-Nov Close out meeting

## Data Management Catalogue DONE (hidden)
Consultant: | Neha | Project: | Data Management Catalogue DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Current - Creating More User Instructions for different categories
| Current Project State | Current
| Deliverable currently being worked on | Creating More User Instructions for different categories
| Overall Notes/Comments | 1-Nov Close out meeting

## Social Media Prospect Log In DN (hidden)
Consultant: | Neha | Project: | Social Media Prospect Log In DN
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Future - To-Be Process for student applicant journey
| Current Project State | Future
| Deliverable currently being worked on | To-Be Process for student applicant journey
| Overall Notes/Comments | 2-Nov close out meeting

## MSW - DONE (hidden)
Consultant: | Paritosh | Project: | MSW - DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes | Peer review for quality
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Future - Nill
| Current Project State | Future
| Deliverable currently being worked on | Nill
| Overall Notes/Comments | FINISHED | https://drive.google.com/drive/folders/1XL0jsz_JYZywGzdkoNHOJRpZPHFMxIks

## CQU Success - DONE (hidden)
Consultant: | Paritosh | Project: | CQU Success - DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Current - Nil
| Current Project State | Current
| Deliverable currently being worked on | Nil
| Overall Notes/Comments | Project is done given that there is no funding

## Release Management - DONE (hidden)
Consultant: | Paritosh | Project: | Release Management - DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Current - Nil - Project stopped due to complexity and scope
| Current Project State | Current
| Deliverable currently being worked on | Nil - Project stopped due to complexity and scope
Overall Notes/Comments

## DONE Attraction & Conversion (hidden)
Consultant: | Vandana | Project: | DONE Attraction & Conversion
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes | PM Reviewed, awaiting Shaune's review
| Is Work Plan saved | Yes | Jira extract
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes | 28-Sep - Louis to update after a practice run with Vandana. We can then look at if further Collab prac workshop is required or what is needed to uplift in this area. 10-Oct Louis f/u Vandana was showing signs of improvement on different smaller meetings.
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Other - Nil
| Current Project State | Other
| Deliverable currently being worked on | Nil
| Overall Notes/Comments | Project is finished

## Ticketing System-DONE (hidden)
Consultant: | Bryant | Project: | Ticketing System-DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes | No updates
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Recommendation -
| Current Project State | Recommendation
Deliverable currently being worked on
| Overall Notes/Comments | Service is now complete

## VET Apprentice Block-DONE (hidden)
Consultant: | Arlene | Project: | VET Apprentice Block-DONE
BAPL delivery documentation on google drive |  | Green | Comments
| Is SDS saved | Yes
| Is Work Plan saved | Yes
| Are weekly status reports sent | Yes
| Is Status Report saved | Yes
Consultant Performance |  | Green
| Is the consultant deliverables of quality | Yes
| Is the consultant updating deliverables based on feedback | Yes
| Is the consultant using their time wisely | Yes
| Does the consultant have good professional attitude | Yes
| Can the consultant facilitate on their own? | Yes
Client Performance |  | Green
| Does the PM provide assistance | Yes
| Is the client culture up to BAPL standards (for example: SME's are approachable and provide information) | Yes
Current Deliverable |  | Other - Work Complete. Close out meeting next week (4-Sep)
| Current Project State | Other
| Deliverable currently being worked on | Work Complete. Close out meeting next week (4-Sep)
| Overall Notes/Comments | Work completed. Close out meeting completed including agreement from PM and Senior BA to be used a referee and testimonial partner